## CE AP 2019 review
Energy - reduce energy demand, improve energy efficiency and convert to renewable, low or zero carbon technologies for energy and heat needs
Action Proposed 2019 | Delivered | Comment | CE AP review 2023 | CE AP New Text
Estimate the current renewable energy generation within Bridport, set targets for reduction in energy demand and monitor annually. |  | Proved too complicated to find accurate data to use in target setting. No further action planned. | REMOVE
Exert pressure on Dorset Council and housing developers to include a renewable micro grid as part of Vearse Farm development |  | Included as part of BTC submission to the Foundry Lea Design Panel and in comments on the reserved matters process. | REMOVE
Support will be given to ‘climate smart’ initiatives where the outcomes encourage the community to reduce, reuse, repair, and recycle products |  | Used to inform development of BTC policies, actions and comments on planning matters. | RETAIN
Support will be given to community scale energy conservation measures, including retro-fit, where local support and viability has been demonstrated |  | Used to inform development of BTC policies, actions and comments on planning matters. | RETAIN
Support development of the local woodfuel sector by encouraging sustainable timber extraction, hedgerow management, and new planting for both fuel and amenity, and as a means of addressing fuel poverty |  | Supported. | REMOVE
Work with Dorset Community Energy to promote community and commercial renewable installations in Bridport and consider the merits of establishing a new Bridport Community Energy Company |  | BTC supports Energy Local Bridport, the first Energy Club in the UK | AMEND | merge with other actions supporting domestic pv installations and extension of Energy Local Bridport capacity to take on more low income H/hs
Campaign for new build standards to ensure all new homes are ultra-efficient and use low carbon heating from 2025 |  | Used to inform development of BTC policies, actions and comments on planning matters. | RETAIN
Work with Magna Housing to promote retro fit energy conservation to the social rented sector in Bridport |  | BTC has engaged with Magna and involved them in the BTC led energy champions programme. | RETAIN
Work with social enterprises to push domestic PV installations in Bridport – for example Solar Streets |  | BTC has supported Transition Town Bridports' work on pushing for more domestic pv installation. | AMEND | merge with other actions supporting domestic pv installations and extension of Energy Local Bridport capacity to take on more low income H/hs
Work with social enterprises to push commercial PV installation – for example Green Nation |  | No activity undertaken to date. | REMOVE
Work with Colfox School on Energy Sparks scheme to help reduce carbon |  | No activity undertaken to date. | REMOVE
Transport – Support sustainable modes transport, transition to low carbon vehicles and strategic planning to reduce need for car travel
Action Proposed 2019 | Delivered | Comment
Support the installation of quick charging electric car points where local support or viability has been demonstrated |  | Both Dorset Council and BTC have installed ev charging points in town car parks, with plans for more. | RETAIN
Campaign for a car free day or car free evenings (Fri & Sat eve, 18.00 to 24.00, when shops closed) |  | No activity undertaken to date. | REMOVE
Work with Dorset Council to extend/ improve cycle/ walking network (see BANP policies and plans) |  | Bridport Area Neighbourhood Plan includes a plan for improvements to the cycling/ walking network. BTC identifed option for greener Access & Movement in 2021 | RETAIN
Work with a social enterprise to establish a Bridport Car Club |  | BTC worked with Co-Cars to undertake surveys and develop a funding proposal. No further action due to funding issues. | REMOVE
Work with Minerva Trust to promote a Car Sharing Scheme in Bridport for school and work journeys. |  | No activity undertaken to date. | REMOVE
Collaborate with other town and parish councils to exert pressure on Dorset Council to provide and promote increased public transport as a viable alternative to private car use. Lobby national government for funding for rural areas to support this aim. |  | BTC supports WATAG and is a member of DCAN | RETAIN
Food & Land Use - promote sustainable land management, including tree planting to help absorb carbon & water and encourage healthy eating and recreation.
Action Proposed 2019 | Delivered | Comment
Support development of a Woodhub in Bridport as a Timber Fabrication Workspace and driver for more active woodland management and use of locally sourced timber in construction |  | BTC supports the woodhub proposal developed by Wessex Community Assets for co-location at the Foundry Lea Skills Academy. | RETAIN
Research and publish a Tree Plan for Bridport – what sorts oftrees are needed, where best to plant? Aim to increase town tree cover from current 12% to align with Government target of 17% by 2035 |  | Bridport Area Tree Plan – Bridport Town Council (bridport-tc.gov.uk) | REMOVE
Support commitment to ban landfill of biodegradable waste by 2025 |  | Support offered but no actions.
Work with businesses to procure more food and other biomaterials from Dorset. Commitments should be set out in purchasing guidelines and procurement policies |  | Support offered but no actions. | AMEND | More specific wording on how procurement will contribute to the global climate emergency. | Proposal to use a green clause to future proof high environmental performance/ sustainablity in any agreement about land use or long term contract with suppliers.
Work with Dorset Wildlife Trust to promote land management that maximises re wilding & tree planting opportunities |  | BTC has reviewed all mangement plan for its green spaces in light of the climate emergency. Extensive tree planting has been undertaken in collaboration with Bridport Tree Grou. BTC supported a new project to instal Dipper Boxes on the River Brit/Asker. | AMEND | DWT and Others..
Work with the Bridport Community Fridge scheme and offer support to food re-use groups |  | BTC supports a number of Food Groups in the Town. | AMEND | merge actions to be more specific resupport Food Security Plan and Local Food Festival | Perhaps a new action better articulating the need to strengthen the local food system ( food Security Plan) and support community resilience..
Support stronger links between food producers, local organisations, shops to promote local food and avoid food waste |  | BTC supports the Local Food Festival as well as the establishment and work of Bridport Food Matters. | AMEND
Economic, Housing & Waste – support the local economy and ensure homes are climate proofed whilst reducing, re using and recycle materials
Action Proposed 2019 | Delivered | Comment
Work with Dorset Waste Partnership for enhanced recycling with greater clarity on what is recycled, where it’s recycled & how it’s recycled |  | Support offered but no actions. | REMOVE
Work with the Neighbourhood Plan JCC and parishes to promote climate SMART housing policies and actions |  | Support offered but no actions. | AMEND | merge with other actions supporting low carbon building
Work proactively with Bridport Business Chamber to promote: a ban on SUP use/ promote locally produced goods & services/energy reduction measures (i.e. keeping doors shut in winter |  | BTC has supported local busineeses in meeting requirements for a Plastic Free Town. | REMOVE
Work with Wessex Community Assets and local Community Land Trust to support low carbon solutions for social housing, including retrofit and new build. |  | Support provided to Bridport Area Community Housing (BACH) CLT and to the Raise the Roof project. | AMEND | merge with other actions supporting low carbon building
Work with local tourism businesses to undertake assessments of the carbon impacts of the visitor economy and develop carbon reduction programmes. |  | No activity undertaken to date. | REMOVE
Work with Transition Town Bridport and others to produce a directory of services and advice promoting reduction, re-use |  | No activity undertaken to date. | REMOVE
Citizen Engagement - to engage local people in accelerating the response to the climate emergency whilst building resilience to future climate impacts
Action Proposed 2019 | Delivered | Comment
Develop the existing One Planet Living Working Group to monitor delivery of the Climate Emergency Action Plan. |  | No activity undertaken to date. | REMOVE
Run themed ‘climate conversations’ with local people as deliberations on this action plan and key climate action questions. |  | BTC has suported a number of housing and energy events through the Energy Champions programme and support for BACH. | AMEND | merge actions and add specifc detail around supporting energy champions
Promote use of carbon calculators/SMART meters for householders to help drive behavioural change. |  | BTC Energy Champions programme. | AMEND
Provide ‘free to resident’ climate emergency awareness training focused on practical responses and actions – for example stalls at local events. |  | No activity undertaken to date. | AMEND
Engaging artists to better visualise the transformations required |  | Climte Action was the theme for the Bridport Sculpture Trail in 2021. | AMEND | specific link to commissioning artworks for the town
Bridport ‘Think and Do’ programme to connect and activate the community through pop ups, events, exhibitions, webinars and projects designed, led and run by committed individuals or groups. This would take place in partnership with Dorset Council, residents, schools, businesses, and the whole community.

## CE AP 2023
CLIMATE MITIGATION - EMISSIONS REDUCTION
Action Proposed 2023 | Measure | Responsibility | Priority
Improve energy efficiency and de carbonise energy supply
Support ‘climate smart’ initiatives where the outcomes encourage the community to reduce, reuse, repair, and recycle products. | Number of schemes/planning applications supported | Planning Committee Town Clerk
Support community scale energy conservation measures, including retro-fit, where local support and viability has been demonstrated. | Number of schemes/planning applications supported | Planning Committee Town Clerk
Work with Dorset Community Energy and others to promote community and commercial renewable installations in Bridport and support roll out of Energy Local Bridport to more households. | Number of renewable installations completed Increase in number of Energy Local Bridport members | Environment and Social Well Being Committee Energy Champions
Work with Magna Housing to promote retro fit energy conservation of the social rented sector in Bridport. | Number of retrofit installations completed Number of Magna Housing residents joining Energy Local Bridport | Environment and Social Well Being Committee Energy Champions
Support national campaigns for low carbon building standards to be mandatory. | Evidence of input to campaigns/ lobbying | Planning Committee Town Clerk
Drive emissions reduction from surface travel, buildings and land use
Work with Dorset Council to extend/ improve cycle/ walking network (see BANP policies and plans) - Prioritise a new Foundry Lea cycle/walking link. | Km of new or upgraded cycling/ walking infrastructure installed | Planning Committee Town Surveyor
Support installation of rapid charging electric car points where local support or viability has been demonstrated. | Number of new ev chargers installed | Planning Committee Town Surveyor
Collaborate with other town and parish councils to exert pressure on Dorset Council to provide and promote increased public transport as a viable alternative to private car use. | Improved public transport routes/ frequency/ timetables. | Planning Committee Town Clerk
Lobby national government for funding for rural areas to support improved public transport. | Evidence of input to campaigns/ lobbying. | Planning Committee Town Clerk
Work with Wessex Community Assets and local Community Land Trusts to support low carbon solutions for social housing, including retrofit and new build. | Number of social housing schemes completed | Planning Committee Town Clerk
Support development of a Fibre Hub in Bridport as a fabrication Workspace for locally sourced bio materials. | New fabrication workspace created Volume of bio material grown and processed | Environment and Social Well Being Committee Community Projects Manager
Introduce a clause to future proof high environmental performance/ sustainablity in any agreement about land use or long term contract with suppliers. | Environmental standard incorporated into leases/ procurement | Finance and General Purposes Committee Town Surveyor
CLIMATE ADAPTATION - RESILIENT, SOCIALLY INCLUSIVE and HEALTHY COMMUNITIES
Support the piloting of the Bridport Learning Hub to drive skills and training required for net zero transition. | Number of learners supported Number of training events delivered | Environment and Social Well Being Committee Community Projects Manager
Support recruitment and training of volunteer flood wardens to better respond to flood events and educate residents about water. | Number of volunteer wardens recruited Number of training sessions run | Environment and Social Well Being Committee Community Projects Manager
Support delivery of the Bridport Food Security Plan - land under horticultrual production, new food enterprises, stronger local food supply chains. | Ha of new horticulture production Number of new food enterprise start ups | Environment and Social Well Being Committee Community Projects Manager
Education and Awareness
Support community energy champions to help drive behavioural change around energy use and generation. | Number of community energy champions Number of energy champion run training events | Environment and Social Well Being Committee Community Projects Manager
Establish a Bridport think and do inititive that provides support to community led climate/ ecological projects - a variation on BTC grant focused soley on climate action. | Number of climate emergency community projects funded | Environment and Social Well Being Committee Community Projects Manager
THE ECOLOGICAL EMERGENCY
Support Bridport Tree Group and others to increase tree cover in and around the town and deliver the Bridport Tree Plan. | Number of trees planted pa | Environment and Social Well Being Committee Community Projects Manager
Work with Dorset Wildlife Trust, Dorset AONB and others to support landscape scale nature recovery in and around Bridport. | Ha land under long term nature recovery management | Environment and Social Well Being Committee Community Projects Manager
Greenspace management plans to prioritise nature. | Ha of land managed for wildlife | Environment and Social Well Being Committee Town Surveyor
Support establishment, training and operation of water quality monitoring of river Brit and Asker. | Number of volunteer trained and sites monitored | Environment and Social Well Being Committee Community Projects Manager
TRANSITION TO A CIRCULAR ECONOMY
Actively support a shift in the way we think about and use materials and start to build a circular economy — eliminating waste by reusing, refurbishing, recycling, and recirculating for as long as possible. It offers more durability to consumers, reduces waste and pollution, and helps to regenerate nature. | Amend BTC procurement policies to favour keeping products circulating in use longer. Prioritise durability, recyclability, and reuse. Only use recycleable packaging and demand similar from BTC suppliers - using packaging made from mono-material plastics, bioplastics, and paper. | Full Council All Staff
Funding secured or not required to action
Requires new funding to action
Requires action by others and new funding to action